## Sheet1
| Namratha S | Srivatsa Raju S | Veena B
DATE | TASK | TASK | TASK
Week1(July18-July22)
2016-07-18 | List of Topic | List of Topic | List of Topic | Listing of Topic
2016-07-19 | Selection of Topic | Selection of Topic | Selection of Topic | Selection of Topic
2016-07-20 | Search About Types Of Emotions | Search About Types Of Emotions | Search About Types Of Emotions
2016-07-21 | Discuss with guide | Discuss with guide | Discuss with guide
2016-07-22 | Topic Finalize | Topic Finalize | Topic Finalize
2016-07-23 | Topic Disucssion | Topic Disucssion | Topic Disucssion
2016-07-24 | Sunday
Week 2 (July 25- July31)
2016-07-25 | Topic Disucssion | Topic Disucssion | Topic Disucssion
2016-07-26 | Topic Disucssion | Topic Disucssion | Topic Disucssion
2016-07-27 | Topic Disucssion | Topic Disucssion | Topic Disucssion
2016-07-28 | Finalizing of Topic | Finalizing of Topic | Finalizing of Topic
2016-07-29 | Holiday | Holiday | Holiday
2016-07-30 | Holiday | Holiday
2016-07-31 | Holiday
Week 3 (Aug 01- Aug 07)
2016-08-01 | Mentor Suggestion | Mentor Suggestion | Mentor Suggestion | Mentor Suggestion
2016-08-02 | Discussion about Topic | Discussion about Topic | Discussion about Topic
2016-08-03 | Consolidating the collected information | Consolidating the collected information | Consolidating the collected information | Consolidating the collected information
2016-08-04 | Mentor Suggestion | Mentor Suggestion | Mentor Suggestion | Listing the features of IOT
2016-08-05 | Discuss about Ontology | Discuss about Ontology | Discuss about Ontology | Usage of IOT
2016-08-06 | Mentor Suggestion | Mentor Suggestion | Mentor Suggestion
2016-08-07
Week 04 (Aug 08- Aug 14)
2016-08-08 | Find IEEE papers About Ontology | Find IEEE papers About Ontology | Find IEEE papers About Ontology | Literature On raspberry Pi
2016-08-09 | Discussion about IEEE Ontology papers | Discussion about IEEE Ontology papers | Discussion about IEEE Ontology papers
2016-08-10 | Find IEEE papers About Ontology | Find IEEE papers About Ontology | Find IEEE papers About Ontology | Learning about connection of Raspberry Pi
2016-08-11 | Discussion about IEEE Ontology papers | Discussion about IEEE Ontology papers | Discussion about IEEE Ontology papers | Referring IEEE paper for project
2016-08-12 | Guide Review | Guide Review | Guide Review
2016-08-13 | Discussion about IEEE Ontology papers | Discussion about IEEE Ontology papers | Discussion about IEEE Ontology papers
2016-08-14
Week 05 (Aug 15- Aug 21)
2016-08-15
2016-08-16 | Mentor Suggestion | Mentor Suggestion | Mentor Suggestion
2016-08-17 | Search for abstracts | Search for abstracts | Search for abstracts
2016-08-18 | Search for abstracts | Search for abstracts | Search for abstracts
2016-08-19 | Consolidating the collected information | Consolidating the collected information | Consolidating the collected information
2016-08-20 | Guide Review | Guide Review | Guide Review
2016-08-21
Week 06 (Aug 22- Aug 28)
2016-08-22 | Find IEEE base papers About Ontology | Find IEEE base papers About Ontology | Find IEEE base papers About Ontology
2016-08-23 | Consolidating the collected information | Consolidating the collected information | Consolidating the collected information
2016-08-24 | Mentor Suggestion | Mentor Suggestion | Mentor Suggestion
2016-08-25 | Discuss about Methos Of Emotion | Discuss about Methos Of Emotion | Discuss about Methos Of Emotion
2016-08-26 | BOF session | BOF session | BOF session
2016-08-27 | Guide Review | Guide Review | Guide Review
2016-08-28
Week 07 (Aug 30- Sep 04)
2016-08-29 | FirstNakuri Test | Take Guidelines to proceed further | Take Guidelines to proceed further
2016-08-30 | Freshers world Test | Take Guidelines to proceed further | Take Guidelines to proceed further
2016-08-31 | Guide Suggestion | Group discussion | Group discussion
2016-09-01 | Internals
2016-09-02 | Holiday
2016-09-03 | Internals
2016-09-04
Week 08 (Sep 05- Sep 11)
2016-09-05 | Holiday | Holiday | Holiday
2016-09-06 | Holiday | Holiday | Holiday
2016-09-07 | Internals | Internals | Internals
2016-09-08
2016-09-09 | Guide Suggestion about Git hub | Learning about usage of Git hub | Learning about usage of Git hub
2016-09-10 | Learning about usage of Git hub | Consolidating the collected information | Consolidating the collected information
2016-09-11
Week 09 (Sep 12- Sep 18)
2016-09-12 | Learning about usage of Git hub | Learning about usage of Git hub | Learning about usage of Git hub
2016-09-13 | Learning about usage of Git hub | Learning about usage of Git hub | Learning about usage of Git hub
2016-09-14 | Guide Review | Guide Review | Guide Review
2016-09-15 | Consolidating the collected information | Consolidating the collected information | Consolidating the collected information
2016-09-16 | Host a File | Host a File | Host a File
2016-09-17 | Make a repository | Make a repository | Make a repository
2016-09-18
Week 10 (Sep 19-Sep 25)
2016-09-19 | Discuss about ProgramingLanguage | Discuss about ProgramingLanguage | Discuss about ProgramingLanguage
2016-09-20 | Guide Review | Guide Review | Guide Review
2016-09-21 | Finalizing Programing Language | Finalizing Programing Language | Finalizing Programing Language
2016-09-22 | WBD structure | SRS | SRS
2016-09-23 | Discuss about WBD structure | Discuss about WBD structure | Discuss about WBD structure
2016-09-24 | Discuss about SRS | Discuss about SRS | Discuss about SRS
2016-09-25
Week 11 (Sep 26- Oct 2)
2016-09-26 | Distrubute Work | Distrubute Work | Distrubute Work
2016-09-27 | Working On WBD | Working On SRS | Working On SRS
2016-09-28 | Group Discussion | Group Discussion | Group Discussion
2016-09-29 | Working On WBD | Working On WBD | Working On SRS
2016-09-30 | Guide Review | Guide Review | Guide Review
2016-10-01 | Job Mela | Job Mela | Job Mela
2016-10-02
Week 12 (Oct 3- Oct 9)
2016-10-03 | WBD structure Changes
2016-10-04 | Guide Review | Guide Review | Guide Review
2016-10-05 | Orientation Programme | Orientation Programme | Orientation Programme
2016-10-06 | Internals | Internals | Internals
2016-10-07 | internals | internals | internals
2016-10-08 | internals | internals | internals
2016-10-09
Week 13 (Oct 10- Oct 16)
2016-10-10 | Searching IEEE paper based on ontology | Searching IEEE paper based on emotion analysis | Searching IEEE paper based on emotion mining
2016-10-11 | Analysing IEEE paper | Analysing IEEE paper | Analysing IEEE paper
2016-10-12 | Analysing IEEE paper | Analysing IEEE paper | Analysing IEEE paper
2016-10-13 | Guide Review | Guide Review | Guide Review
2016-10-14 | Group Discussion | Group Discussion | Group Discussion
2016-10-15 | Agile Revision | Agile Revision | Agile Revision
2016-10-16
Week 14 (Oct 17- Oct 23)
2016-10-17
2016-10-18 | finalizing for review | finalizing for review | finalizing for review
2016-10-19 | Guide Review | Guide Review | Guide Review
2016-10-20
2016-10-21
2016-10-22
2016-10-23
Week 14 (Oct 24- Oct 30)
2016-10-24
2016-10-25
2016-10-26
2016-10-27
2016-10-28
2016-10-29
2016-10-30
2016-10-31
2016-11-01
2016-11-02
2016-11-03
2016-11-04
2016-11-05
2016-11-06
2016-11-07
2016-11-08
2016-11-09
2016-11-10
2016-11-11
2016-11-12
2016-11-13
2016-11-14
2016-11-15
2016-11-16
2016-11-17
2016-11-18
2016-11-19
2016-11-20
2016-11-21
2016-11-22
2016-11-23
2016-11-24
2016-11-25
2016-11-26
2016-11-27
2016-11-28
2016-11-29
2016-11-30
2016-12-01
2016-12-02
2016-12-03
2016-12-04
2016-12-05
2016-12-06
2016-12-07
2016-12-08
2016-12-09
2016-12-10
2016-12-11
2016-12-12
2016-12-13
2016-12-14
2016-12-15
2016-12-16
2016-12-17
2016-12-18
2016-12-19
2016-12-20
2016-12-21
2016-12-22
2016-12-23
2016-12-24
2016-12-25
2016-12-26
2016-12-27
2016-12-28
2016-12-29
2016-12-30
2016-12-31
2017-01-01
2017-01-02
2017-01-03
2017-01-04
2017-01-05
2017-01-06
2017-01-07
2017-01-08
2017-01-09
2017-01-10
2017-01-11
2017-01-12
2017-01-13
2017-01-14
2017-01-15
2017-01-16
2017-01-17
2017-01-18
2017-01-19
2017-01-20
2017-01-21
2017-01-22
2017-01-23
2017-01-24
2017-01-25
2017-01-26
2017-01-27
2017-01-28
2017-01-29
2017-01-30
2017-01-31
2017-02-01
2017-02-02
2017-02-03
2017-02-04
2017-02-05
2017-02-06
2017-02-07
2017-02-08
2017-02-09
2017-02-10
2017-02-11
2017-02-12
2017-02-13
2017-02-14
2017-02-15
2017-02-16
2017-02-17
2017-02-18
2017-02-19
2017-02-20
2017-02-21
2017-02-22
2017-02-23
2017-02-24
2017-02-25
2017-02-26
2017-02-27
2017-02-28